## Sheet1
Identification of Risks for TCHS Project
Sr No | Risks | Options | Likelihood of occurence | Mitigants
1 | Inexperience of consultants in managing projects | Self | 20% | At the outset, we will make every attempt to select experienced and expert consultants. In spite of this, if any consultant is found to be weak, we have the option to change that consultant, in the self option. In the builder option, we will not even know if any consultant is weak. The builder decides everything.
2 | Plans not passed in Auto DCR | All | 10% | If the plans are not passed in the Auto DCR, then we will have to get the plans passed as per the normal procedure. AutoDCR is a shortcut which we can use.
3 | Permission to raise Deep Discount bond not given by Deputy Registrar | All | 10% | Deep Discount Bond has already been discussed with the Deputy Registrar, and he has given an in-principle approval for the same. The chance of this happening is very low.
4 | Poor response to the tender from Contractors | All | 40% | This means that our terms and conditions are too stringent and may have to be toned down. We will then need to scale down our demands. Altenately, if the response is good, we may even be able to scale up our demands, or negotiate better terms.
5 | Contractors not agreeable to the concessions proposed by PMC | All | 20% | All terms and conditions in all tenders, will be as decided by the GB, not the PMC. Every tender will be approved by the GB before release, and they will be fair to both parties. If a contractor is agreeable to the terms, we will look for a cotractor who is agreeable.
6 | Dispute between PMC and their associates | Self | 10% | All contracts with PMC's associates will be executed between the associate and TCHS. Thus, if there is a dispute between PMC and their associates, our contract with them will be insulated from the dispute. Even if PMC exits the project (worst-case scenario), the project will continue with another PMC.
7 | Associates disengaging from the project midway | Self | 30% | This is a risk that exists in every project. Any consultant or contractor can threaten to exit the project at any time. In the self optio, the standard mitigation for this is to execute multiple individual contracts with each consultant or contractor. This limits every contractor's hold over the project only to his scope of work, and this reduces the threat. In the builder option, the entire responsibility is given to one contractor. If he disengages from the project for any reason, the only option is the legal option.
8 | MHADA certifying lesser area than the estimates | All | 0% | It has been reported by all who have experience in redevlopment projects, that MHADA includes the corridor and staircase areas and divides it equally amongst the flats on that floor. We have considered only the carpet areas of the flats in our calculations. Hence the chances that the certified areas will reduce from these numbers, is very low. In fact, we expect the certified areas to be higher than our calculated areas.
9 | Delay in permissions for plan approvals from local authorities | All | 30% | We will approach the authorities with our application through an experienced consultant, who understands the process, procedures and costs involved in the approval process. This is the best mitigation plan for this risk. The government has put in several checks to ensure that there is no undue delay in approvals.
10 | Stringent conditions in the Government sanction | All | 10% | The conditions have been clearly spelt out in various government websites, and we will comply with all of them, including some which are in the pipeline. However, if for any particular reason the authorities decide to be stricter than those conditions, we will ask our consultant to handle the situation. The trend at present is to simplify the procedure and dilute the conditions, rather than make them more stringent.
11 | FSI Area sanctioned is less than that envisaged | All | 10% | For FSI calculations, we have complied with all the conditions imposed in the DCPR 2034. Some area has also been kept as reserve in our calculations. If the area sanctioned is even lesser than that, we will have to forgo some area from our lobby or clubhouse. The possibility of this happening is quite remote.
12 | Members approaching Deputy Registrar against the project | All | 60% | We cannot rule out the possibility. we will try and accomodate all reasonable wishes of our members and tenants. Since we have complied with all rules applicable, it will be difficult for the Deputy Registrar to rule against the project. We are also continuously in touch with the Deputy Registrar to check that the steps that we are planning, have his tacit approval.
13 | Occupants refusing to vacate the flats | All | 30% | Usually a consent letter is obtained from all members and tenants before start of the project. This usually happens because builders offer very low rent assistance to members. In our self option, we have considered generous rent assistance for all members and tenants. Hence, we do not anticipate this to happen in our project.
14 | Family disputes while vacating the flats | All | 20% | Our lawyer may be consulted about the possible legal options. The general rule during redevelopment is that the societ deals with the member whose name appears in the records of the society. Any family dispute, if existing, can proceed independently.
15 | Delay in getting the unsecured loan in our account | Self | 20% | Liquidated Damages clause will be part of Standard Terms and Conditions in our contracts, and will also be applicable to the contract with the financiers.
16 | Identification of contractor for construction | All | 0% | Actually, this is not a risk. This is a task, and can be addressed through quick actions and quick decisions.
17 | Non availability of construction material | All | 20% | Non-availability of raw materials is usually not included in the Force Majeure conditions, for the construction company. If non-availability of construction materials is part of the Force Majeure conditions in our Standard Terms and Conditions, then we have the option of increasing only that relevant rate for construction for as long as the scarcity exists, or wait for the scarcity to ease.
18 | Non availability of adequate skilled labour | All | 10% | Skilled labour is always available; it is the price that the contractor is willing to pay. Our contract with the construction compay will be on the basis of the Bill Of Quantities. Non-availability of labour will not change that.
19 | Critical labour diverted midway through the project to another project by the contractor | All | 10% | A clause to prevent this can be inserted in our contract, and will be inserted. Our project is a simple residential building, and no special critical labour will be needed for this project.
20 | Poor quality of material received | All | 30% | TCHS will employ a Construction Management Agency (which will be loyal to TCHS), and who will be given the task of inspecting all the material received, and who will be empowered to reject sub-standard material. Additionally, a vigilance committee consisting of minimum two members from the Sub-Committee or members of the General Body (plus backups) will be formed to monitor the activities of the site Construction Management Agency.
21 | Force majeure - Rain, Earthquake, flood, fire, riots | All | 10% | Force Majeure clause is a standard condition in all contracts, to accept a delay in case of an Act of God. There is no mitigation for an Act of God. We will have to deal with it accordingly, at that time.
22 | Low productivity of labour | All | 20% | Our contract with the Constructor will be BOQ based. If he does not deliver, he does not get paid. Low productivity of labour is the Constructor's problem. The contructor has to replace the labour quickly, if he expects to get paid.
23 | Breakdown of machinery | All | 30% | Our contract with the Constructor will be BOQ based. If he does not deliver, he does not get paid. Breakdown of machinery is the Constructor's problem. He will have to replace the defective machine quickly, if he expects to get paid for the work.
24 | Labour issues | Builder | 20% | Our contract with the Constructor will be BOQ based. If he does not deliver, he does not get paid. Labour issues are the Constructor's problem.
25 | Air pollution | All | 50% | Suitable clauses will be inserted in the Constructor's contract to adhere to all the pollution control norms that are imposed upon us by the authorities. The Construction Management Agency will be given the respnsibility of ensuring this at all times.
26 | Noise pollution | All | 20% | Suitable clauses will be inserted in the Constructor's contract to adhere to all the pollution control norms that are imposed upon us by the authorities. The Construction Management Agency will be given the respnsibility of ensuring this at all times.
27 | Coordination between different construction department | Self | 40% | That is the task of Project Management, and the SC expects to play that role. It is not a risk. We can even employ a Project Manager, should we feel the need to do so. In a builder option, it is to be handled by the builder; we have no control over this.
28 | Accidents | All | 20% | Our contracts will have a clause indemnifying TCHS against accidents, but this point to be discussed with our lawyer also. In either self or builder option, TCHS cannot free itself of the liability. The Construction Management Agency will have the task of ensuring that all safety norms are adhered to by the contractors.
29 | Dispute between contractors | All | 30% | The Project Management team will have to resolve any disputes that arise between contractors so that they do not negatively impact the project. In the self option, that authority will be with us. In the builder option, we have no control.
30 | Delay in project execution | All | 40% | Every contract will have a Liquidated Damages clause in it. But the Project Team will have to manage the project so that unnecessary delays are avoided. The Construction Management Agency that will be appointed by TCHS will also assist in this.
31 | Bookings less than expected | Self | 30% | This will remain as unsold inventories with TCHS. TCHS may decide to rent them out to earn a steady icome, or decide to sell this inventory at the then prevailing market prices.
32 | Applicants who have booked backing out | Self | 40% | Applicants will have to be suitably disincentivised from backing out, but it is possible that some applicants may back out in spite of this. This will add to the unsold inventory.
33 | Design issues | Builder | 10% | Proper standards will be adhered to while designing all structures of the rehab complex. Additionally, TCHS will appoint a Structural Engineering Auditor company to review and vet all the designs submitted to ensure compliance with safety and all applicable and relevant standards. In the builder option, we will have no control on this.
34 | Stoppage of work by local politicians, goons | All | 40% | This has to be handled by the Constructor company. They know how to deal with this. TCHS can take no responsibility in this matter. Our payment terms with the construction conmpany will be on the basis of completed work.
35 | Mobilization of sufficient resources on time and within budget | Builder | 30% | Our contracts will have some part payment as Mobilization Advance. This will not be paid to the contractor, unless the agreed mobilisation happens.
36 | Cartel formation by other developers | Builder | 50% | TCHS will have to ensure that this does not happen by bringing in new contractors who are not part of the cartel. That is the standard and only way to break any cartel.
37 | Difficulty in identification of TCHS team to oversee the project | All | 20% | TCHS will form a Project Team dedicated to overseeing this project. The SC will arrange this. The Construction Management Agency will be a part of the Project Team. We will request help from willing GB members too.
38 | Identify the incidence of taxes on the members and TCHS from the various financial transactions | All | 10% | We have appointed a tax consultant and another GST consultant to ensure that the project strictly adheres to all tax laws applicable, and includes any changes that ouccur during the execution of the project.
39 | Unlimited liability of TCHS | All | 30% | The legal opinion on this is that in the case of self-redevelopment, TCHS has more liability than in the builder option. In the case of the builder option, TCHS is considered as a co-Promoter, and cannot divest itself of all liabilities.
40 | Incidence of stamp duty | Builder | 30% | Opinion from the tax consultant to be obtained on this. We will consider stamp duty in our project cost.
41 | Dependence of a few key honorary members | All | 20% | Project team is being created with overlapping skills so that backups are available, when needed.
42 | Commitment of SC members | All | 0% | Present SC members are extremely committed and capable. Improved after the reconstitution of the SC. If needed, more members will be included.
| Commitment of MC members | All | 40% | We believe the MC members are very committed to this project, and do not consider this as a risk.
43 | Minutes of meeting of the Sub-Committee | All | 0% | It has been agreed that the Sub-Committee will write minutes of their meetings and submit to the Managing Committee, for uploading on the wbsite.
44 | Managing tenants of Building no. 16 and KSA | Builder | 10% | We have appointed tenant representatives from buildings no 16 and KSA, and they are doing very well as part of our Sub-Committee. This problem may arise in the case of the builder option, if the builder does not offer equal advantages to the tenants as given to the members.
45 | Sale component in rehab complex | All | 0% | All surplus carpet area after accounting for the necessary flats and amenities, will be created as additional flats and will be handed over to the Managing Committee to do whatever it wishes to, rent it or sell it. This Project cannot decide what that Managing Committee should do with it.
46 | Amalgamation of plots of KSA and TCHS | All | 10% | Information about exact procedure will be obtained from lawyer, and due process will be followed
47 | Professional fees of consultants may eat into the profits of the project | Self | 0% | Professional fees are one part of the project cost, as much as cost of material or any other services that we acquire. The profit of the project is arrived at after evaluating all costs and deducting it from the realisation.
48 | Non-adherence to applicable laws | Builder | 0% | In the self option, we have agreed that we adhere to all applicable laws. Hence, this is not a risk. In the builder option, we will not even know if he has adhered to all the laws. Non-adherence to laws by the builder can surface even ten years after our project is complete, and there is nothing we can do about it.
49 | Legal action against builder for illegal actvity in some other, unrelated project | Builder | 0% | In the self option, this is not a risk. In the builder option, this can very well happen, and or project can grind to a halt, due to this. There is nothing we can do about this.
50 | Owners don’t have proper documents or they are old/lost/ not transfered | All | 20% | This is a risk. We will assist all members who do not have the necessary papers so that they are not inconvenienced.
51 | Owners/members can change their minds about the amenities or flat size/ design | All | 10% | All amenities will be clearly discussed with the memberas and tenants before finalisation. We will take the opinions of everyone for this. In the builder option, the builder decides these. The members have no choioce.
52 | Members don’t get the agreement vetted by their lawyers and then get into trouble | Builder | 70% | It is almost mandatory that members have to get any agreement vetted by their lawyers, particularly in the case of the builder option. In the case of self-redevleopemnt, there is still some scope to rewrite the agreement, as it is an agreement between ourselves.
53 | Increase in premium charges | All | 10% | Premium charges are set by the government and have to be paid by all, whih come under that category. The likelihood of this happening is low, as the government is active,y promoting self-redevelopment.
54 | Increase in rent | All | 30% | In the self option, we will of course pay the increased rent. This may reduce our total corpus amount by a few crores, or may covered through contingency. In the builder option, the rent amount and tenure is fixed at the time of signing the agreement. Increasing either or both, is entirely dependent on the builder
55 | Stay brought by neighbouring societies due to noise or dust or damage to property | All | 30% | This cannot be ruled out completely. Please see the planned mitigation for points 25 and 26.
56 | Certain members refuse to shift or vacate premises | All | 10% | A PAAA agreement is signed by every member before demolition can start. Thus, the likelihood of this risk is low.
57 | No proper walking or vehicular path if partly demolished buildings | All | 0% | We plan to relocate all residents before demolition starts.
58 | Inexperienced Contractors | All | 20% | In self option, the General Body members select all major consultants and contractors. The Sub-Committee will ensure that only experienced consultants and contractors are presented to the GB for selection. In the builder option, the members have no choice. The builder selects all consultants and contractors.
59 | Poor super vision | All | 50% | In the self option, a Construction Management Agency will be appointed to supervise all activities at site. Thus, the members are assured of proper supervision and regular updates. In the builder option, members have no choice. They have to depend on the builder's supervisors
60 | Lack of experienced and proper staff | All | 20% | In the RSC, we have people with adeqate experience in project management. In the builder option, we have no conrol on this.
61 | No detailed drawings and change of drawings during the project( promise one thing and finished product is different or altered) | All | 20% | The RSC will ensure that we get complete and detailed drawings and documents from each consultant. The Structural Engineering Auditor will ensure completeness and accuracy of all documents. RSC will also ensure, via the Construction Management Consultant, that the construction follows what is is specified in the dorawings and documents. Members will be allowed access to our site to so that they can also be assured that the construction follows whatever has been promised. In the builder option, usually the builder does not permit site access. It is a simply a matter of faith. On the builder.
62 | No proper site inspections and supervision | All | 20% | The Construction Management Consultant will ensure that proper inspections and site supervision happens. He gets paid only for this, and reports to TCHS.
63 | Improper management of project | All | 20% | Between the RSC and the Construction Management Consultant, this can be managed effectively. In the builder option, we have no control.
64 | Delay in revision of designs | All | 10% | TCHS will always get documents and drawings in their original editable form. If any consulant then delays the revision, TCHS can get it done urgently, through the Structuiral Engineering Auditor or an external agency.
65 | Delay in getting necessary permissions and approvals | All | 20% | We have contacts in the government departments, which can be activated to expedite permissions and approvals.
66 | More money spent than required or necessary for various tasks leading to the project completion | Self | 40% | Periodic review of all planned expenses will be carried out with subject experts to ensure that they are realistic.
67 | Improper structural audits | All | 30% | That’s why the Structural Engineering Auditor is planned to be appointed, by the RSC. In the builder option, we have no control.
68 | Lack of labourers or equipment needed for construction | All | 20% | Lack of labourers has been dealt with in point 18 above. Regarding eqipment, it is important that we select a construction company which can speed up project progress with equipemtn, should this become necessary. In the builder option, we have no control.
69 | Accidents on the premises during the project | All | 5% | This can be prevented by proper safety procedures being followed by reputed construction companies. We should select only such companies. This is possible only when we retain control of our project. Our Construction Management Consultant will have the authority to stop work immediately if any unsafe practice is followed. Contractually, we can hold the construction company liable for the accident. In the builder option, we have no such control. As a co-promoter of the project, TCHS will always some liability in both options. That cannot be eliminated.
70 | Contractors Abandon the project midway due to bankruptcy or disputes within their company or with society | All | 30% | Since the project is split into multiple parts, and farmed out to multiple contractors, the impact of this risk can be minimised. That particular contractor or copnsultant can be replaced. In the builder option, there is only one contractor, and replacing that contractor is very lengthy process.
71 | Corruption or government instability | All | 20% | This can be mitigated by persuasion through contacts, which we have. The builder also does the same, but through money, which ultimately is charged to the project.
72 | Violation of bylaws | Builder | 0% | We have agreed that in self option, we will follow all applicable bylaws. In the builder option, we have no option. Violation of bylaws can affect even many years after the project is complete.
73 | Disputes between members/tenants | All | 10% | If we carry our tenants along with us, and accept their just demands, we see no reason for this risk to occur. We can instill this spirit of cooperation amongst all, members as well as tenants, and minimse this risk to zero.
74 | Illegal construction/hence demolitions | Builder | 40% | Simliar to point 72. We have decided that no bylaws will be violated, and hence no illegal constructions will be carried out. In the builder option, this is a very real risk, and can haunt us several years after the project is complete.
75 | New redevelopment rules brought in by government negating older rules | All | 0% | So far, it has been seen that all governements are extremely favourable to the Self option. Hence, all revisions of the laws give more benefits to the self option. The government, at the same time, is trying to discourage the builder option. Builders usually insert change of laws as an option in the Force Majeure conditions, so that they can reduce their liabilty with this excuse.
76 | Increase or fluctuations in Cost of project | All | 30% | This is usually mitigated by having enogh contigency margin in the project costing. Builders also do this but if the cost increase affects their profit, they prefer to delay the project until the selling prices of the flats increases to their expected values.
77 | Legal stays brought in by members or neighbouring societies | All | 20% | This is a risk that we need to resolve at the members/ tenants level. Satisfy everyone is the mantra that we should follow. In the builder option, some builders even instigate certain members to go legal to bring about a stay. This helps them to manage delays in the project, due to other reasons, and increase prices.
78 | Not able to sell constructed flats
79 | Select wrong type or model of redevelopment
80 | Value of project or flats calculated wrongly
81 | PMC inexperienced or wrongly chosen
82 | Height restriction of buildings
83 | No conveyance
84 | Disputes between society or members with individual appointed contractors
85 | Lack of organisation and unity between MC and RSC
86 | Lack of communication between members and consultants
87 | Loans not available without mortgaging land
88 | No proper legal documentation and agreements between society and consultants or members
89 | Delay in payments
90 | Delay in project completion due to finance
91 | Increase in Cost of construction
92 | Cash payments to certain government officials for permissions
93 | Death or severe illness of builder/consultants
94 | Loose total control of land and design to builder
95 | Give road access to builder/builders - in the bargain loose privacy of society
96 | Self redevelopment is a new concept compared to builder which is tried and tested
97 | Self redevelopment - members get more area and more corpus
98 | Control is fully with society
99 | All plans and documents are in the name of the society
100 | Profits of the project is shared between all members
101 | Plans and amenities can be discussed and decided by the members
102 | *Appeal to Members of Co-operative Housing Societies involved in their Building's Redevelopment Process*
103 | Managing Committee and Assenting Members should thoroughly evaluate the preferred Developer's financial status, project capacity, past performance, and litigation history before proceeding with Redevelopment Agreements, Ignoring these checks can lead to severe consequences under the provisions of the Indian Contract Act & RERA.
104 | If builder fails to complete construction-on-time-the consumer court holds the builder-liable
105 | In Redevelopment Project, Managing Committees sign and submit Mandatory *Form B* to the RERA Authority, assuming all liabilities on behalf of the Developer.
106 | *Form B* is mandatory to be submitted by the Managing Committee for the developer to obtain a RERA registration number, which is essential for selling saleable units in the open market.
107 | Actually Developers often hide the details of *Form B* while sigining Development Agreement and further don’t even inform the members about it, even up to the demolition of buildings.
108 | After receiving the Plinth CC, Developers pressure the Managing Committee to sign *Form B*, sometimes threatening to stop paying monthly rent to members if they refuse.
109 | If the project fails for any reason, Buyers of the Saleable units can claim compensation from the housing society (CHS) also.
110 | in case the Project fails, the Members could face financial losses, including the risk of losing their properties and further paying compensation to the Saleable Components Buyers from their own pockets.
111 | choosing a financially weak and inexperienced Developer almost 100% guarantees project failure.
112 | To avoid such risks, members must ensure a transparent process and carefully choose a Financially Strong and experienced Developer to protect their investments and avoid future liabilities of the Saleable Components Buyers Investment.
113 | Builders bribe or have a setting with MHADA to increase the area of construction while taking measurements-case has happened in our neighbourhood